## NMS
Task | Start_Date | End_Date | Status | Remark
Kick Start | 2025-08-13 | 2025-08-13 | Completed
Gap analysis | 2025-08-18 | 2025-08-29 | In Progress | Analysis of CN vs. KLN Web
Initial Scope and Dev Schedule | 2025-08-22 | 2025-08-22 | To Do | Plan for devlopment schedule
Technical Review | 2025-08-22 | 2025-09-18 | To Do
Mock UI | 2025-09-01 | 2025-09-18 | To Do
User Briefing Sessoin | 2025-09-09 | 2025-09-11 | To Do | Around 2 Sessions; Introduce the core function and plan for customized feature(s)
Dev - Option 1 (Tentative) | 2025-09-19 | 2025-10-03 | To Do | First option for earlier development if possible
Dev - Option 2 (Tentative) | 2025-10-09 | 2025-10-24 | To Do | Second option for devlopment schedule
SIT | 2025-10-27 | 2025-10-31 | To Do | Depends on Dev schedule
UAT | 2025-11-03 | 2025-11-14 | To Do | Depends on Dev schedule; War Room will be set
Sign off & Deployment preparation | 2025-11-17 | 2025-11-21 | To Do | Depends on Dev schedule
User Training | 2025-11-03 | 2025-11-21 | To Do | Depends on Dev schedule
Ready to Go Live | 2025-11-24 | 2025-11-24 | Target Go Live | Depends on Dev schedule

## NMS (Initial)
Task | Start_Date | End_Date | Status | Remark
Kick Start | 2025-08-13 | 2025-08-13 | Completed
Gap analysis | 2025-08-18 | 2025-08-29 | In Progress | Analysis of CN vs. KLN Web
Initial Scope and Dev Schedule | 2025-08-22 | 2025-08-22 | To Do | Plan for devlopment schedule
Mock UI Preparation and Confirmation | 2025-09-01 | 2025-09-18 | To Do
Technical & Design Review (Tentative) | 2025-09-19 | 2025-09-30 | To Do | First option for earlier development if possible
User Briefing Sessoin | 2025-10-02 | 2025-10-07 | To Do | Around 2 Sessions; Introduce the core function and plan for customized feature(s)
Dev (Tentative) | 2025-10-09 | 2025-10-24 | To Do | Second option for devlopment schedule
SIT | 2025-10-27 | 2025-10-31 | To Do
UAT | 2025-11-03 | 2025-11-14 | To Do | War Room will be set
Sign off & Deployment preparation | 2025-11-17 | 2025-11-21 | To Do
User Training | 2025-11-03 | 2025-11-21 | To Do
Ready to Go Live | 2025-11-24 | 2025-11-24 | Target Go Live